## Sheet1
Category | Feature Name | Description | Status | Backend Support | Frontend Support | Client Support | Priority | Gap & Missing Details
Fleet Management | Live Fleet Overview | Real-time robot status health and firmware version monitoring over WebSockets | Real | Full | Full | Full | P0 | Production ready with live heartbeat updates
Fleet Management | Device & Attachment Registry | Hardware identity, serial numbers, chassis HW revisions, lifecycle states, and telemetry-reported CAN bus tool modules | Real | Full | Full | Full | P0 | Production ready: tracks chassis lifecycle (Active/Maintenance/Decommissioned), tags, automated CAN bus tool detection, and dynamic HW revision compatibility verification
Fleet Management | Zero-Touch Provisioning | Automated self-registration of robots and attached tools upon initial boot | Real | Full | Full | Full | P0 | Working in simulator and server; needs client security tokens
Fleet Management | Connectivity & Device Shadow | Reported vs desired state synchronization and cellular/WiFi signal diagnostics | Simulated | None | Mock UI | None | P1 | No device shadow document sync engine (AWS IoT style), signal RSSI is faked in UI
OTA Updates | Firmware Version Catalog | Upload management and version scanning for robot and Jetson compute binaries | Real | Full | Full | Partial | P0 | Multipart tar.gz uploads working; protected by firmware:upload RBAC permission; lacks SHA256 checksum signing
OTA Updates | One-Click Fleet Deployment | Targeted rollout trigger across selected or all robots with live progress tracking | Real | Full | Full | Full | P0 | Working for Robot and Jetson channels; protected by deploy:trigger RBAC permission
OTA Updates | Attachment Firmware OTA | Independent firmware deployment and version tracking for attachments (Mower/Plow/etc.) | Real | Full | Full | Partial | P0 | Backend and UI working; standalone client script doesn't simulate attachment updates
OTA Updates | Campaigns & Phased Rollouts | Multi-stage rollout waves (canary 1% -> 10% -> 50% -> 100%) with failure rate monitoring | Simulated | None | Mock UI | None | P1 | No phased wave scheduling, failure threshold monitoring, or auto-halt logic in backend
OTA Updates | One-Click & Auto Rollback | Automated revert to last known stable firmware on boot failure or error spike | Missing | None | None | None | P1 | No rollback API endpoint, backup partition tracking, or auto-revert triggers
Diagnostics & Debug | Remote Hardware Diagnostics | Engineering diagnostic dispatch (MCU self-test, CAN bus query, crash log dump, safe reboot, return to dock, emergency partition reset) | Real | Full | Full | Full | P0 | Production ready: bi-directional command queue (/api/robot/{id}/command), device-side execution in simulator, RBAC permission gating, live engineering terminal & telemetry policy
Diagnostics | Real-Time Telemetry | Battery voltage, motor current, CPU thermals, and vibration time-series streams | Simulated | None | Mock UI | None | P0 | No telemetry ingestion endpoint (/api/robot/telemetry) or time-series database; UI generates pseudo-random sparklines
Diagnostics | Fault Codes & Diagnostic Logs | Diagnostic Trouble Codes (DTCs), fault severity tracking, and error log dumps | Simulated | None | Mock UI | None | P1 | No fault reporting API; UI renders hardcoded FAULT_CODES constant array
Diagnostics | Predictive Maintenance | Component wear estimation and fleet failure risk scoring | Simulated | None | Mock UI | None | P2 | Heuristics are calculated client-side from robot online duration; no ML wear model
Diagnostics | Alerts & Incident Management | Real-time threshold-based alert routing and incident acknowledgement | Simulated | None | Mock UI | None | P2 | Browser-only alert filtering; lacks email/webhook/SMS integrations or persistent alert state
Platform & Support | Support Console | Customer support diagnostics, robot search, and remote device inspect drawer | Partial | Partial | Partial | None | P2 | Search filters local in-memory array; lacks remote log retrieval and service ticketing
Platform & Support | Automation Engine | If-this-then-that operational rules (e.g. auto-dock on low battery or weather alert) | Missing | None | Mock UI | None | P2 | Static placeholder page; no rule evaluation engine or scheduled trigger service
Platform & Support | Access Control & Audit Trail | Role-Based Access Control (RBAC), user authentication, session management, and live security audit logs | Real | Full | Full | Partial | P0 | Implemented JWT auth, PBKDF2 hashing, 5 distinct roles, login page, topbar profile, and live audit logging. Next: OAuth2/SSO & DB persistence
Platform & Support | Enterprise Multi-Tenancy | B2B organization isolation, customer fleet partitioning, and partner API access | Partial | Partial | Partial | None | P1 | Organization schemas and IDs defined in RBAC claims; needs database partitioning per tenant
Diagnostics & AI | The Data Flywheel | Continuous learning loop: Field telemetry -> Cloud Insights -> Firmware OTA -> Improved Fleet | Partial | None | Full | None | P2 | Visual animated Canvas topology in dashboard; counters read basic fleet state rather than real ML pipeline
Client Daemon | Embedded Agent Flashing Engine | Physical A/B partition flashing, firmware binary extraction, and rollback guard | Missing | None | N/A | None | P0 | robot_client.py only simulates sleep() delays; no real package verification, download, or execution
Database & Infra | Persistent Database Backend | Production database migration from flat JSON file to relational/time-series DB | Partial | Partial | N/A | N/A | P0 | Persists to single fleet_db.json file with synchronous disk rewrites; needs SQLite/PostgreSQL